## KPI Checklist
Phase / Activity | Status | Task | Start date | End date | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) | Informed status | Responsible Roles | Name | Key Questions | Nuances / Pitfalls | Comment
Phase 0: Strategic Preparation |  | Approve strategic goals |  |  | Executive Leadership | Executive Leadership | KPI Project Lead, Department Heads | Entire management team |  | KPI Project Lead |  | – What are the top 2–3 goals we must achieve this year? – What decisions should KPI data influence? – Which systems already collect data, and how trustworthy are they? – Who will own data integrity & KPI validation? | Strategy may be vague or misaligned Data can be “dirty” or incomplete Teams (IT / operations) may not be involved early
|  | Tie KPI to strategic goals |  |  | KPI Project Lead | Executive Leadership | Operations Heads, Analytics | Department Leads |  | IT / Data Engineer
|  | Assemble KPI core team |  |  | KPI Project Lead | Executive Leadership | HR, Department Heads | All involved units |  | Change Management
|  | Audit existing data sources |  |  | IT / System Architects / Data Engineers | KPI Project Lead | Operations, Maintenance, Quality | Executive Leadership |  | Executive Leadership / Plant Director
|  | Diagnose data quality / readiness |  |  | Data Engineers / Data Quality Team | KPI Project Lead | IT, Operations | Executive Leadership
|  | Plan communications & change management |  |  | Change Management Lead / KPI Project Lead | Executive Leadership | Department Heads, HR | All employees in scope
Phase 1: KPI Design |  | List candidate KPI |  |  | Operations Managers + Analysts | KPI Project Lead | Process Engineers, Quality | Department Heads |  |  |  | – Does this KPI drive a decision or just report a number? – How often must the KPI update to be useful? – Which exceptions (downtime, changeovers, outages) must we handle? – What assumptions go into the formula? | Too many KPIs → diluted focus Formulas may be impractical to compute Reliance on manual data introduces errors KPIs may “jump” — need smoothing, anomaly control
|  | Classify into leading vs lagging KPI |  |  | Analysts / Process Engineers | KPI Governance | Operations, BI Team | Executives
|  | Define KPI specs (formula, source, thresholds) |  |  | Analysts / Data Engineers | KPI Project Lead | Operations, Quality, Maintenance | Executive Leadership
|  | Select core KPI set (3–7) |  |  | KPI Governance / Project Lead | Executive Leadership | Department Heads, Analysts | All Units
|  | Prototype calculations on historical data |  |  | Analysts / Data Engineers | KPI Project Lead | Operations, Quality | Executive Leadership
|  | Stress-test KPI definitions |  |  | Analysts / Data Engineers | KPI Governance | Operations, Maintenance | Department Heads
Phase 2: Pilot / Testing |  | Select pilot area / line |  |  | Plant / Line Manager | KPI Project Lead | Operations, Maintenance | Executive Leadership |  |  |  | – What values seem anomalous, and why? – Do operators understand what the KPI means and what actions to take? – How do we respond to alerts or warnings? – What if a process change ruins KPI consistency? | A pilot in a “nice” zone may mask problems Operators may ignore KPIs if seen as “management tools” Process changes may break KPI logic People may “optimize to the metric,” not the real goal
|  | Launch KPI pilot |  |  | Pilot Lead + Line Manager | KPI Project Lead | Operators, Supervisors | Department Heads
|  | Collect user feedback |  |  | Pilot Lead / Change Management | KPI Project Lead | Operators, Supervisors | Executives, Department Heads
|  | Compare KPI results with manual / historical records |  |  | Analysts / Process Engineers | KPI Project Lead | Operations, QA | Executive Leadership
|  | Detect anomalies & formula errors |  |  | Data Quality / Analytics Team | KPI Governance | IT, Operations | Management
|  | Tune / correct KPI definitions |  |  | Analysts / Process Engineers | KPI Governance | Operations, Quality | Executive Leadership
|  | Train users on KPI interpretation & actions |  |  | Training / Change Management | KPI Project Lead | Analysts, Supervisors | All KPI users
|  | Set alert / threshold rules |  |  | Analysts / Operations Managers | KPI Project Lead | Maintenance, IT | Supervisors, Department Heads
Phase 3: Deployment / Scaling |  | Automate data collection & integration |  |  | IT / Integration Team | IT Director / KPI Project Lead | Analytics, Operations | Executive Leadership |  |  |  | – How will KPIs be incorporated into regular review meetings? – What triggers corrective action if KPI falls below a threshold? – Who is accountable for exceptions / adjustments? – When and how will KPIs be revisited / revised? | Systems may face performance issues Conflicts between departments over metrics KPI use might turn into micromanagement Metrics may become ignored if they fall below expectations
|  | Set access control / role permissions |  |  | IT Security / Governance | KPI Project Lead | Department Heads, BI | All Users
|  | Build dashboards / visualizations |  |  | BI / Dashboard Developers | KPI Project Lead | Operations, Analytics | Executive Leadership
|  | Embed KPI in review meetings / processes |  |  | Department Heads / Plant Management | KPI Project Lead | Supervisors, Analysts | All relevant stakeholders
|  | Monitor data quality continuously |  |  | Data Quality / Analytics Team | KPI Governance | IT, Operations | Executive Leadership
|  | Establish KPI review / revision policy |  |  | KPI Governance / Steering Committee | Executive Leadership | Analysts, Operations | All Participants
|  | Document guidelines, instructions, SOPs |  |  | Documentation / Process Team / Analysts | KPI Project Lead | Operations, IT | All Users
Phase 4: Support & Evolution |  | Audit KPI correctness periodically |  |  | Analytics / Data Quality Team | KPI Governance Committee | IT, Operations | Executive Leadership |  |  |  | – Which KPIs must be reconsidered or replaced within 12 months? – Are there recurring data issues or anomalies? – What irritations or friction do users report? – How to better tie KPI domains (finance, quality, operations)? | KPIs may become obsolete Personnel may revert to old manual reports Integrations degrade over time Insufficient maintenance support
|  | Validate data inputs & sources |  |  | Data Engineers / Data Quality | Analytics Lead / Governance | IT, Maintenance | Department Heads
|  | Detect drift / anomalies in KPI trends |  |  | Analysts / Process Improvement | KPI Governance | Operations, Quality | Department Heads
|  | Adjust KPI definitions / thresholds |  |  | Analytics / Process Engineers | KPI Governance | Operations, Quality, IT | Executive Leadership
|  | Add or retire KPI |  |  | KPI Governance / Analytics | Executive Leadership / Steering | Operations, Finance, Quality | All relevant stakeholders
|  | Train new hires & refresh users |  |  | Training / Change Management | KPI Governance / Program Lead | Analytics, Department Leads | New Users, All Users
|  | Governance reviews & oversight |  |  | KPI Governance Committee | Executive Sponsorship / Steering | Analytics, Operations, IT | Stakeholders
|  | Integrate KPI with adjacent domains |  |  | Functional Analysts / Analytics | KPI Governance / Executive | Department Leads (Finance, Quality, Supply) | Executive Leadership

## Contact list
Team Contacts
Role | Name | Email | Phone
Executive Leadership / Plant Director
KPI Project Lead
Change Management Lead
IT / Systems Architect / Data Engineers
Data Quality Team Lead
Operations Managers
Analysts / KPI Modelers
Process Engineers
Quality Department Lead
Maintenance Department Lead
HR / Organizational / Training Lead
BI / Dashboard Developers Lead
IT Security / Governance Lead
Pilot Lead
Line / Area Manager
Operators / Supervisors (representatives)
Documentation / Process Team Lead
KPI Governance / Steering Committee Chair
Finance Department Lead
Supply Chain Department Lead
Functional Analysts (Finance, Quality, Supply domains)